## Product Backlog
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | 1, 2, 3 | High | D | 15
4 | As a pilot, I want to be able to enter information about my aircraft so that potential passengers can see that information. | 2, 3 | Low | D | 3
5 | As a pilot, I want to be able to enter my professional qualifications/type ratings so that I can accurately represent my experience. | 2, 3 | Medium | D | 3
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | 1, 2, 3 | High | D | 10
8 | As an account holder, I want to be able to enter my contact information so that I don’t have to enter it every time I book a flight. | 2 | High | D | 3
10 | As a potential passenger, I want to be able to see which pilots are based at the airports near me so that I can see all my possible options nearby. | 2022-04-05 | High | W | 15
13 | As a potential passenger, I want to be able to contact the pilot so that I can ask questions or negotiate the price before the trip takes place. | 2022-04-05 | Medium | W | 10
24 | As a pilot I want to be able to contact the passengers so that I can answer questions, negotiate or give advice before a trip takes place. | 2022-04-05 | Medium | W | 10
33 | As a passenger I want to be able to schedule a booking so that I can keep track of the date, time, fare, aircraft, and route. | 2022-05-06 | High | W | 10
32 | As a passenger I want to be able to make direct payments to a pilot account that I have scheduled a booking with so that I can cover the costs of the trip. | 2022-05-06 | High | W | 7
40 | As a passenger, I want to be able to cancel a booked trip so that I don’t have to go on a previously planned trip. | 2022-05-06 | Medium | W | 5
34 | As a passenger, I want to be able to get fully refunded when I cancel a trip before a set date so that I don’t waste my money. | 2022-05-06 | Medium | W | 5
12 | As a potential passenger, I want the ability to search using multiple parameters so that I can find listings that best match what I am looking for. | 6 | Medium | W | 20
16 | As a recent passenger, I want to be able to write a review of the experience after the trip so that future passengers can get a sense of the quality of ride expected. | 6 | Low | W | 3
15 | As a pilot, I want to be able to view my upcoming trips with a schedule planner so that I can plan when to be at an airport. | 7 + | Medium | W | 10
14 | As a potential passenger, I want to be able to see how many seats are currently available so that I can book a flight with available seating. | 7 + | Medium | W | 4
21 | As a pilot, I want to be able to post not only my home airport, but where I frequently go/ where I can go so that my listing reaches a wider audience of potential passengers. | 7 + | Low | W | 5
17 | As a passenger account holder, I want to be able to view reviews regarding the service from other passengers so that I can accurately decide if I am interested in a specific service. | 7 + | Low | W | 3
18 | As a pilot account holder, I want to be able to receive reviews regarding the service so that I can better the experience for future passengers. | 7 + | Low | W | 3
11 | As a potential passenger, I want to be able to view a map that shows listings so that I can see the available pilots at different airports. | 7 + | Medium | W | 25
36 | As a pilot, I would like to view my flight path in a flight history so that I don’t have to track it myself. | 7 + | Medium | W | 15
28 | As a pilot, I would like to view my flight price in a flight history so that I don’t have to track it myself. | 7 + | Low | W | 1
29 | As a pilot, I would like to view my flight date in a flight history so that I don’t have to track it myself. | 7 + | High | W | 1
30 | As a pilot, I would like to view my passengers in a flight history so that I don’t have to track it myself. | 7 + | High | W | 1
9 | As a potential passenger, I want to allow my location to be tracked so that I can view listings at airports near me. | 7 + | Low | W | 15
22 | As a potential passenger, I want to be able to have easy access to pricing information so that I can quickly determine if a listing is within my budget. | 7 + | Low | W | 7
26 | As a passenger I would like to see the most popular rated destinations by other passengers so that I can take that into consideration when making my decision. | 7 + | Low | W | 10