## Sprint Backlog
ID | User Story | Story Tasks | Sprint # | Sprint Goal | Story Types | Story Points | Story Points Completed | Names and % Contribution
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a new application on React | 1 | Set up the development environments in this sprint so we can begin software development and implementation in the next sprint | T | 1 | 1 | Christian 50%, Johnny 50%
|  | Create a new github repository, environments and kanban |  |  | T | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
|  | Begin knowledge aquisition on building databases |  |  | KA | 1 | 1 | Christian 100%
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | Create a mock-up UI | 1 | Have a basic UI mockup that we can reference when we begin implementation of the software | KA | 1 | 1 | Elliot 100%
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a database that stores user information | 2 | Have the foundations of an initial user interface and begin research on the secure storage of account information | KA, T | 6 | 2 | Christian 75%, Johnny 25%
|  | Start to generate a basic user interface |  |  | KA, F | 6 | 3 | Christian 60%, Orion 20%, Allison 20%
|  | Knowlege Aquisition on secure account handling |  |  | KA | 3 | 3 | Christian 100%
4 | As a pilot, I want to be able to enter information about my aircraft so that potential passengers can see that information. | Creating a page to allow the users to enter the information to their new account | 2 | Have a way for the user to enter this information when the generate a new account | F | 1 | 1 | Orion 40%, Johnny 40%. Allison 20%
|  | Learning how to use React |  |  | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
5 | As a pilot, I want to be able to enter my professional qualifications/type ratings so that I can accurately represent my experience. | Learning how to use React | 2 | Have a way for the user to enter this information when the generate a new account | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | Knowlege Aquisition on best practices for login systems | 2 | Have a front facing login website that uses secure practices in accordance with industry standards. | KA | 2 | 2 | Christian 100%
|  | Hash Function for storing passwords |  |  | T | 4 | 4 | Christian 100%
|  | Actually creating the UI |  |  | F | 3 | 4 | Eliot 50%, Christian 50%
8 | As an account holder, I want to be able to enter my contact information so that I don’t have to enter it every time I book a flight. | Learning how to use React | 2 | Have a web interface that can accept contact information and a separate web interface that can display contact information. | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%