## Sprint Backlog 1
ID | User Story | Story Tasks | Sprint # | Sprint Goal | Story Types | Story Points | Story Points Completed | Names and % Contribution
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a new application on React | 1 | Set up the development environments in this sprint so we can begin software development and implementation in the next sprint | T | 1 | 1 | Christian 50%, Johnny 50%
|  | Create a new github repository, environments and kanban |  |  | T | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
|  | Begin knowledge aquisition on building databases |  |  | KA | 1 | 1 | Christian 100%
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | Create a mock-up UI | 1 | Have a basic UI mockup that we can reference when we begin implementation of the software | KA | 1 | 1 | Elliot 100%

## Sprint Backlog 2
ID | User Story | Story Tasks | Sprint # | Story Goal | Story Type | Story Points | Story Points Completed | Names and % Contribution
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a database that stores user information | 2 | Have the foundations of an initial user interface and begin research on the secure storage of account information | KA, T | 6 | 2 | Christian 75%, Johnny 25%
|  | Start to generate a basic user interface |  |  | KA, F | 6 | 3 | Christian 60%, Orion 20%, Allison 20%
|  | Knowlege Aquisition on secure account handling |  |  | KA | 3 | 3 | Christian 100%
4 | As a pilot, I want to be able to enter information about my aircraft so that potential passengers can see that information. | Creating a page to allow the users to enter the information to their new account | 2 | Have a way for the user to enter this information when the generate a new account | F | 1 | 1 | Orion 40%, Johnny 40%. Allison 20%
|  | Learning how to use React |  |  | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
5 | As a pilot, I want to be able to enter my professional qualifications/type ratings so that I can accurately represent my experience. | Learning how to use React | 2 | Have a way for the user to enter this information when the generate a new account | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | Knowlege Aquisition on best practices for login systems | 2 | Have a front facing login website that uses secure practices in accordance with industry standards. | KA | 2 | 2 | Christian 100%
|  | Hash Function for storing passwords |  |  | T | 4 | 4 | Christian 100%
|  | Actually creating the UI |  |  | F | 3 | 4 | Eliot 50%, Christian 50%
8 | As an account holder, I want to be able to enter my contact information so that I don’t have to enter it every time I book a flight. | Learning how to use React | 2 | Have a web interface that can accept contact information and a separate web interface that can display contact information. | KA | 1 | 1 | Orion 20%, Christian 20%, Allison 20%, Elliot 20%, Johnny 20%

## Sprint Backlog 3
ID | User Story | Story Tasks | Sprint # | Story Goal | Story Type | Story Points | Story Points Completed | Names and % Contribution
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a database that stores user information | 3 | Have the foundations of an initial user interface and begin research on the secure storage of account information | KA, T | 4 | 4 | Christian 75%, Johnny 25%
|  | Start to generate a basic user interface |  |  | KA, F | 3 | 3 | Orion 100%
4 | As a pilot, I want to be able to enter information about my aircraft so that potential passengers can see that information. | Creating a page to allow the users to enter the information to their new account | 3 | Have a way for the user to enter this information when the generate a new account | F | 1 | 1 | Orion 50%, Johnny 25%, Eliot 25%.
5 | As a pilot, I want to be able to enter my professional qualifications/type ratings so that I can accurately represent my experience. | Create the necessary UI components | 3 | Have the UI completed | F | 1 | 1 | Orion 100%
|  | Link the frontend UI inputs to the database on the backend |  | Have UI inputs reflected in the Firestore database | T | 1 | 1 | Johnny 50%, Eliot 50%.
8 | As an account holder, I want to be able to enter my contact information so that I don’t have to enter it every time I book a flight. | Create the necessary UI components | 3 | Have the UI completed | F | 1 | 1 | Orion 100%
|  | Link the frontend UI inputs to the database on the backend |  | Have UI inputs reflected in the Firestore database | T | 1 | 1 | Johnny 50%, Eliot 50%.

## Sprint Backlog 4
ID | User Story | Story Tasks | Sprint # | Story Goal | Story Type | Story Points | Story Points Completed | Names and % Contribution
10 | As a potential passenger, I want to be able to see which pilots are based at the airports near me so that I can see all my possible options nearby. | Implementation of the list of pilots on home page | 4 | Make sure passengers can see pilots on their account page and send message requests to them | F | 10 | 2 | Elliot 100%
|  | Knowledge aquisition of Displaying database items on the UI |  |  | KA | 5 | 1 | Elliot 100%
13 | As a potential passenger, I want to be able to contact the pilot so that I can ask questions or negotiate the price before the trip takes place. | Knowledge acquisition for messaging applications | 4 | Make sure that passengers can message or otherwise contact pilots which accept to recieve messages from them | KA | 2 | 2 | Christian 100%
|  | Reconfigure firestore database to accomadate messaging applications |  |  | T | 2 | 2 | Christian 100%
24 | As a pilot I want to be able to contact the passengers so that I can answer questions, negotiate or give advice before a trip takes place. | Knowledge acquisition for messaging applications | 4 | Make sure that passengers can message or otherwise contact passenger which as to be able to send messages to them | KA | 2 | 2 | Christian 100%
|  | Reconfigure firestore database to accomadate messaging applications |  |  | T | 2 | 2 | Christian 100%
33 | As a passenger I want to be able to schedule a booking so that I can keep track of the date, time, fare, aircraft, and route. | Create a clalender system to organize bookings | 4 | Make sure that passengers and pilots can collaborate to create and schedule flights, and to make the information of these flights trackable by either account type. | F | 2 | 1 | Johnny 100%

## Spring Backlog 5
ID | User Story | Story Tasks | Sprint # | Story Goal | Story Type | Story Points | Story Points Completed | Names and % Contribution
10 | As a potential passenger, I want to be able to see which pilots are based at the airports near me so that I can see all my possible options nearby. | Implementation of the list of pilots on home page | 5 | Make sure passengers can see pilots on their account page and send message requests to them | F | 8 | 2 | Orion 100%
|  | Knowledge aquisition of Displaying database items on the UI |  |  | KA | 4 | 3 | Orion 100%
13 | As a potential passenger, I want to be able to contact the pilot so that I can ask questions or negotiate the price before the trip takes place. | Knowledge acquisition for messaging applications | 5 | Make sure that passengers can message or otherwise contact pilots which accept to recieve messages from them | KA | 3 | 1 | Christian 100%
|  | Reconfigure firestore database to accomadate messaging applications |  |  | T | 1 | 1 | Christian 100%
24 | As a pilot I want to be able to contact the passengers so that I can answer questions, negotiate or give advice before a trip takes place. | Knowledge acquisition for messaging applications | 5 | Make sure that passengers can message or otherwise contact passenger which as to be able to send messages to them | KA | 3 | 1 | Christian 100%
|  | Reconfigure firestore database to accomadate messaging applications |  |  | T | 1 | 1 | Christian 100%
33 | As a passenger I want to be able to schedule a booking so that I can keep track of the date, time, fare, aircraft, and route. | Implement interactivity on both pilot and passenger accounts to allow them to create bookings | 5 | Make sure that passengers and pilots can collaborate to create and schedule flights, and to make the information of these flights trackable by either account type. | F | 4 | 3 | Johnny 100%