## Sprint Backlog
ID | User Story | Story Tasks | Sprint # | Sprint Goal | Story Types
2 | As a user I want to be able to create an account on FlyAway so that I can utilize the application. | Create a database that stores user information | 2 | Have the foundations of an account management system | T, KA, F
Find a host server to host the website
Knowlege Aquisition on secure account handling
4 | As a pilot, I want to be able to enter information about my aircraft so that potential passengers can see that information. | Create a field within the Account database that can be written to by the user and can be displayed on the Pilot Account | 2 | Have a web interface that can accept aircraft information and a separate web interface that can display aircraft information. | T
Generate the appropriate Divs in the HTML file
5 | As a pilot, I want to be able to enter my professional qualifications/type ratings so that I can accurately represent my experience. | Create a field within the Account database that can be written to by the user and can be displayed on the Pilot Account | 2 | Have a web interface that can accept qualifications and credentials and a separate web interface that can display qualifications and credentials. | T
Generate the appropriate Divs in the HTML file
7 | As an account holder, I want to be able to log into my account using my username and password so that I can securely view details of my booked flight(s) | Knowlege Aquisition on best practices for login systems | 2 | Have a front facing login website that uses secure practices in accordance with industry standards. | KA, F
Hash Function for storing passwords
8 | As an account holder, I want to be able to enter my contact information so that I don’t have to enter it every time I book a flight. | Create a field within the Account database that can be written to by the user and can be displayed on the Pilot Account | 2 | Have a web interface that can accept contact information and a separate web interface that can display contactinformation. | T
Generate the appropriate Divs in the HTML file